## README
DCT Laboratory — Vol II, Ch 9: Stochastic Enterprise Optimization
Seed 26209 · Companion to DCT_V2_Ch09_Lab.ipynb and AXIOM Lab 2.9 (module AXIOM-09). Money in $ million.
Worked Example 9.1, Can a Rule Replace the Committed Delay?, with the book's declarations: Volume I, Chapter 8's law for the digital program on the book's 100,000 paths (seed 8), every answer judged on 100,000 fresh paths (seed 26209, the lab's); and Chapter 8's hiring loop with human resources' record (Sections 9.2-9.3).
Declarations: the law, the levers and their prices, the appetite; the hiring loop's declarations.
Plan: the plan's liquidity and the draw quarter by quarter, the share of the draw still ahead, and the Gaussian chance of a breach in each quarter with their sum (Proposition 9.2(i); Figure 9.1).
Packages: Volume I's package from the critical delays of each line (the quantile form), its standard error on fresh paths, the appetite read quarter by quarter, and the CVaR package (Proposition 9.2).
Samples: the margin bounds of Theorem 9.3(iv) (Chernoff and Hoeffding), standard errors, and the sample-size study of Figure 9.2.
Rules: rules that read cash once or every quarter, their costs from lines, delays and shares slowed, and Table 9.3 (Steps 3-4; Figure 9.3(a)).
Information: the clairvoyant's bound, the early warning's allotment and value, and the law with persistent surprises (Proposition 9.3; Step 5; Figure 9.3(b)).
Hiring: certainty equivalence, caution, vigilance, robustness and the value ledger in closed form (Theorems 9.1-9.2; Proposition 9.1).
Engine values (green) are what needs the simulated paths: critical delays, chances, shares slowed, the rules' triggers, the sample-size study. Everything else is a formula.
Reference_Values and Checks: the engine's numbers and a PASS/FAIL comparison with this workbook's formulas.
LEGEND
Input: blue on pale gold. A declaration from the book; change it to explore.
Formula: black. Recalculates from the inputs.
Engine value: green on pale green. Computed by the notebook's engine (the book's numbers); the Checks sheet compares the workbook's formulas with them.
Cross-sheet link: green.

## Declarations
Declarations (Worked Example 9.1, Step 1; Chapter 8's hiring loop with HR's record). Money in $ million.
Quantity | Value | Source
Liquidity today | 620 | Meridian's state (Volume I, Chapter 1)
$ million per index point | 6.2 | Index 100 = $620 million
Plan without the draw: long-run index | 112 | The Chapter 1 plan relaxes from 100 toward 112
at the rate (a year) | 0.35
The draw's depth (index points) | 28 | The digital program's draw, deepest at two years
The draw is deepest at (years) | 2 | Shape S(t) = (t/2) e^(1 - t/2)
Floor | 350 | The board's floor
Persistence of a surprise a quarter | 0.6 | E' = 0.6 E + w (Volume I, Chapter 8)
Standard deviation of w, a quarter | 50
Funding-window closures a year | 0.1 | About once a decade
Closure size: mean | 120 | Gamma-distributed, never recovered
Closure size: standard deviation | 50
Line fees over the program, per $ of line | 0.03 | About 1 percent a year for three years
A quarter of delay | 8 | The transformation office (Volume I, Worked Example 15.1)
Depth cut by a quarter of delay (points) | 4 | Two quarters of phasing: depth 20
The appetite | 0.05 | At most a 5 percent chance of a breach in some quarter
Paths (the book's, seed 8; fresh, seed 26209) | 100000 | Volume I, Chapter 8's law
Chapter 8's hiring loop, read without the delay, with human resources' record (Online Appendix 9.B.3)
Share of a gap carried over a quarter | 0.9 | Retraining and internal moves close 10 percent
a: the gap closes on its own, a year | 0.42144 | 4 ln(10/9)
b: share of approvals that become engineers | 0.6
Cost of a gap of 100 engineers, a year | 32 | The program office
q = that cost / 100^2 | 0.0032
Premium for approving 400 a year, a year | 20 | Human resources
r = that premium / 400^2 | 0.000125
Hurdle rate a year | 0.1
rho = ln(1 + hurdle rate) | 0.09531
Gap today (engineers) | -100 | 100 short
sigma: departures and early or late starts, sd over a year | 15 | HR's record
A quarter's cohort: standard deviation of its yield | 0.2 | 20 points around 60 percent
s = that sd x sqrt(1/4) | 0.1 | The yield of a quarter's approvals has sd 2s
c: noise that grows with the gap (vigilance) | 0.5 | Theorem 9.2(iv)
Volume I's cautious gain, a year | 2 | Half the gap a quarter
beta = 2a + rho | 0.93819 | Online Appendix 9.B.3: 0.938194

## Plan
The plan, the draw, and the chances quarter by quarter (Section 9.4; Figure 9.1; AXIOM Lab 2.9, step 1)
E_k is Gaussian with mean 0 and variance 50^2 (1 - 0.6^(2k)) / (1 - 0.6^2) (Volume I, Theorem 8.3), so each quarter's chance of a breach from the surprises alone is a formula; the chance over the program needs the paths.
Quarter k | t (years) | Plan index without the draw | Without the draw ($m) | The draw's shape S | $m per point of depth | Planned liquidity ($m) | Draw still ahead, 1 - S | Variance of E_k | Gaussian chance, surprises only | Simulated, surprises only (engine) | Simulated, full law under Volume I's package (engine)
1 | 0.25 | 101.0054 | 626.2333 | 0.29986 | 1.8591 | 574.1777 | 70.01% | 2500 | 0.000367% | 0% | 0%
2 | 0.5 | 101.9265 | 631.9444 | 0.52925 | 3.2814 | 540.0666 | 47.07% | 3400 | 0.05578% | 0.058% | 0.041%
3 | 0.75 | 102.7705 | 637.177 | 0.70059 | 4.3437 | 515.5542 | 29.94% | 3724 | 0.3335% | 0.312% | 0.182%
4 | 1 | 103.5437 | 641.9712 | 0.82436 | 5.111 | 498.8622 | 17.56% | 3840.64 | 0.8152% | 0.796% | 0.467%
5 | 1.25 | 104.2522 | 646.3637 | 0.90937 | 5.6381 | 488.4972 | 9.063% | 3882.6304 | 1.312% | 1.3% | 0.745%
6 | 1.5 | 104.9013 | 650.3883 | 0.96302 | 5.9707 | 483.2082 | 3.698% | 3897.7469 | 1.644% | 1.623% | 0.913%
7 | 1.75 | 105.4961 | 654.0756 | 0.9915 | 6.1473 | 481.9504 | 0.8495% | 3903.1889 | 1.734% | 1.689% | 0.971%
8 | 2 | 106.041 | 657.4541 | 1 | 6.2 | 483.8541 | 0% | 3905.148 | 1.61% | 1.568% | 0.938%
9 | 2.25 | 106.5402 | 660.5494 | 0.99281 | 6.1554 | 488.1978 | 0.7191% | 3905.8533 | 1.351% | 1.371% | 0.848%
10 | 2.5 | 106.9977 | 663.3855 | 0.9735 | 6.0357 | 494.3857 | 2.65% | 3906.1072 | 1.044% | 1.077% | 0.66%
11 | 2.75 | 107.4168 | 665.9839 | 0.94502 | 5.8591 | 501.9279 | 5.498% | 3906.1986 | 0.7531% | 0.788% | 0.516%
12 | 3 | 107.8007 | 668.3646 | 0.9098 | 5.6407 | 510.424 | 9.02% | 3906.2315 | 0.5132% | 0.492% | 0.393%
Planned liquidity at its low point | 481.9504 | $482 million
in quarter | 7 | 7
A quarter of committed delay lifts the deepest point by | 24.8 | $24.8 million, 'up to $25 million'
Surprises only: the worst quarter, Gaussian | 1.734% | 1.73% (simulated 1.69%)
Surprises only: sum over the quarters, Gaussian | 11.17% | 11.2 percent: the union bound of Proposition 9.2(i)
Surprises only: the worst quarter, simulated | 1.689%
Surprises only: some quarter (engine) | 8.403% | 8.4 percent
Between the worst quarter and the sum? | 1 | Proposition 9.2(i)
Full law, Volume I's package: some quarter (engine) | 5% | 5.0 percent
Full law, Volume I's package: the worst quarter | 0.971% | Under 1 percent
No levers, full law: some quarter (engine) | 24.62% | 24.6 percent, though the average path's trough is $460 million
The average path's trough (engine) | 459.9415

## Packages
Committed packages: the quantile, quarter by quarter, and CVaR (Proposition 9.2; Section 9.4; Worked Example 9.1, Step 2)
For each line, the delay that keeps the appetite is the 95th percentile of the delays the paths need (engine); the cost of a package is 0.03 l + 8 phi.
Line | Delay that meets 5% (engine) | Fees | Delay cost | Cost | The cheapest line on the grid | 170 | Volume I's package: $170 million
120 | 1.0038 | 3.6 | 8.0302 | 11.6302 | Its delay (quarters) | 0.66758 | 0.6676
125 | 0.95009 | 3.75 | 7.6007 | 11.3507 | Fees | 5.1 | $5.10 million
130 | 0.90666 | 3.9 | 7.2532 | 11.1532 | Delay cost | 5.3406 | $5.34 million
135 | 0.87143 | 4.05 | 6.9715 | 11.0215 | Cost | 10.4406 | $10.44 million
140 | 0.83116 | 4.2 | 6.6492 | 10.8492 | Chance on the book's paths (engine) | 5% | 5.000%
145 | 0.79395 | 4.35 | 6.3516 | 10.7016 | Chance on the fresh paths (engine) | 4.907% | 4.907%
150 | 0.75961 | 4.5 | 6.0769 | 10.5769 | Standard error of 5% on 100,000 paths | 0.06892% | 0.069 points
155 | 0.73043 | 4.65 | 5.8434 | 10.4934 | Fresh chance below 5%, in standard errors | 1.3494 | 'within 1.3 standard errors'
160 | 0.70664 | 4.8 | 5.6531 | 10.4531
165 | 0.68676 | 4.95 | 5.4941 | 10.4441 | Designed on the fresh paths: line (engine) | 165 | $165 million
170 | 0.66758 | 5.1 | 5.3406 | 10.4406 | delay (engine) | 0.66576 | 0.6658
175 | 0.65482 | 5.25 | 5.2385 | 10.4885 | cost | 10.2761 | $10.28 million
180 | 0.63934 | 5.4 | 5.1147 | 10.5147 | differs from the book's package by | 0.1645 | Costs that differ by less than about $0.2 million cannot be told apart
185 | 0.62677 | 5.55 | 5.0142 | 10.5642
190 | 0.61333 | 5.7 | 4.9067 | 10.6067 | Read quarter by quarter: line (engine) | 60 | 5 percent in each quarter
195 | 0.60393 | 5.85 | 4.8314 | 10.6814 | delay (engine) | 0.0075646 | 0.008
200 | 0.59926 | 6 | 4.794 | 10.794 | cost | 1.8605 | $1.86 million
205 | 0.59312 | 6.15 | 4.745 | 10.895 | chance of a breach in some quarter (engine) | 16.69% | 16.69% (fresh 16.39%)
210 | 0.58839 | 6.3 | 4.7071 | 11.0071
215 | 0.58183 | 6.45 | 4.6546 | 11.1046 | CVaR, the convex safe version: line (engine) | 185 | $185 million
220 | 0.57864 | 6.6 | 4.6291 | 11.2291 | delay (engine, by bisection) | 1.5955 | 1.596
[5 empty] | cost | 18.3142 | $18.31 million
[5 empty] | chance of a breach (engine) | 1.885% | 1.9 percent (fresh 1.85%)
[5 empty] | Convexity buys tractability and gives up | 7.8736 | $7.9 million
[5 empty] | A nonconvex quantile (Online Appendix 9.B): chance of 1 | 0.04 | c = z1 x1 + z2 x2, x_i independent, 1 with chance 0.04
[5 empty] | chance that c > 0 at the midpoint (0.5, 0.5) | 0.0784 | 0.0784
[5 empty] | 95th percentile at (1, 0) and (0, 1) | 0 | 0
[5 empty] | 95th percentile at their midpoint | 0.5 | 0.5: not convex

## Samples
The sample is part of the answer (Theorem 9.3; Figure 9.2; AXIOM Lab 2.9, step 2)
Theorem 9.3(iv), Equation 9.5: a package whose true chance exceeds 5 percent passes a test at 5% - delta on N paths with probability at most e^(-N kappa), kappa = a ln(a/alpha) + (1 - a) ln((1 - a)/(1 - alpha)), a = alpha - delta; Hoeffding's bound is e^(-2 N delta^2), and kappa >= 2 delta^2 (Pinsker).
Paths N | Margin delta | a = alpha - delta | kappa (Chernoff) | e^(-N kappa) | Hoeffding e^(-2N delta^2) | 2 delta^2 | kappa >= 2 delta^2?
100000 | 0.25% | 4.75% | 6.6855e-05 | 0.0012489 | 0.2865 | 1.25e-05 | TRUE
10000 | 0.25% | 4.75% | 6.6855e-05 | 0.51245 | 0.8825 | 1.25e-05 | TRUE
1000 | 1% | 4% | 0.0011267 | 0.3241 | 0.81873 | 0.0002 | TRUE
1000 | 2% | 3% | 0.0048843 | 0.0075645 | 0.44933 | 0.0008 | TRUE
Standard error of an estimated 5 percent chance
Paths N | Standard error (points)
1000 | 0.6892
10000 | 0.21794
100000 | 0.06892
Packages designed on small samples, judged on the fresh 100,000 paths (engine: 200 samples of 1,000 paths, seeds 900000-900199; 100 of 10,000, seeds 900000-900099)
Paths | Margin | Aimed at | Designs | Meet 5% (engine) | Mean true chance (engine) | 90th percentile (engine) | Mean cost (engine) | Cost against the book's package
1000 | 0% | 5% | 200 | 38.5% | 5.209% | 6.23% | 10.185 | -0.25557
1000 | 1% | 4% | 200 | 87% | 4.21% | 5.085% | 12.0864 | 1.6458
1000 | 2% | 3% | 200 | 100% | 3.225% | 3.851% | 14.3276 | 3.887
10000 | 0% | 5% | 100 | 69% | 4.881% | 5.151% | 10.5259 | 0.085309
10000 | 0.25% | 4.75% | 100 | 97% | 4.639% | 4.891% | 10.9724 | 0.5318
Designed on 1,000 paths and aimed at the appetite, packages look cheaper than the book's and buy too little: an optimistic answer (Theorem 9.3(iii)). The board's test of record is the check on fresh paths.

## Rules
Rules that read cash: one reading, every reading, and Table 9.3 (Worked Example 9.1, Steps 3-4; Figure 9.3(a); AXIOM Lab 2.9, step 3)
A slowdown of phi' quarters decided at the end of quarter k costs 8 phi' (1 - S_k) on each path it slows. Which paths a rule slows, and what that does to the chance of a breach, needs the paths (engine); the costs are formulas.
Quarter read | Draw still ahead | Slow only: line (engine) | Slowdown | Trigger ($m, engine) | Share slowed (engine) | Cost | Commit and slow: line (engine) | Committed | Slowdown | Trigger ($m, engine) | Share slowed (engine) | Cost | Saves against the package
1 | 70.01% | 170 | 1 | 683.4502 | 98.52% | 10.618 | 165 | 0.6 | 0.25 | 572.1282 | 44.9% | 10.3788 | 0.061829
2 | 47.07% | 165 | 1.75 | 615.0344 | 90.12% | 10.8894 | 165 | 0.6 | 1.25 | 478.1692 | 11.64% | 10.2979 | 0.1427
3 | 29.94% | 175 | 4 | 537.9072 | 64.26% | 11.4064 | 165 | 0.55 | 2.5 | 460.7748 | 14.75% | 10.2334 | 0.20718
4 | 17.56% | 180 | 6.5 | 541.8882 | 75.61% | 12.3057 | 165 | 0.6 | 4 | 430.068 | 9.881% | 10.3054 | 0.13525
5 | 9.063% | none | none | none | none | none | 160 | 0.65 | 7 | 409.2548 | 6.871% | 10.3487 | 0.091887
6 | 3.698% | none | none | none | none | none | 170 | 0.65 | 5.75 | 407.865 | 7.575% | 10.4289 | 0.011751
The best quarter to read (least cost of committing and slowing) | 3 | Quarter 3: earlier says too little, later leaves too little of the draw to cut
Its cost | 10.2334 | $10.23 million
It saves against Volume I's package | 0.20718 | $0.21 million
Every reading: slow by 1.25 quarters the first time cash falls more than the margin below the committed plan
Quarter first slowed | Share of paths (engine) | Draw still ahead | Share x draw ahead
1 | 7.348% | 70.01% | 0.051446
2 | 7.879% | 47.07% | 0.03709
3 | 6.821% | 29.94% | 0.020423
4 | 6.11% | 17.56% | 0.010732
5 | 5.325% | 9.063% | 0.0048261
Line (engine search) | 165 | $165 million
Committed delay (engine search) | 0.5 | Half a quarter
Slowdown (engine search) | 1.25 | 1.25 quarters
Margin below the plan's path (engine, by bisection) | 72.6309 | $73 million
Share of paths slowed | 33.48% | A third
Contingent delay on average (quarters) | 0.15565 | 0.16 quarter
Cost | 10.1952 | $10.20 million
Saves against Volume I's package | 0.24544 | $0.25 million
as a share of it | 2.351% | 2 percent
On the fresh paths: chance (engine) | 4.948% | 4.95%
On the fresh paths: cost (engine) | 10.2134 | $10.21 million
Table 9.3: ways of keeping Meridian's appetite, designed on the book's 100,000 paths
Way | Line | Committed delay | Slowdown | Paths slowed | Cost | Fresh: chance (engine) | Fresh: cost (engine)
Volume I's package | 170 | 0.66758 | -- | -- | 10.4406 | 4.907% | 10.4406
Slow only, reading quarter 1 | 170 | 0 | 1 | 98.52% | 10.618 | 4.899% | 10.6201
Slow only, reading quarter 3 | 175 | 0 | 4 | 64.26% | 11.4064 | 4.954% | 11.4109
Commit and slow, quarter 3 | 165 | 0.55 | 2.5 | 14.75% | 10.2334 | 4.961% | 10.2404
Commit and slow, every quarter | 165 | 0.5 | 1.25 | 33.48% | 10.1952 | 4.948% | 10.2134
Early warning of closures | 0, 215 | 0.61, 0.50 | -- | -- | 6.3226
Every path's future |  |  |  |  | 0.4367

## Information
Price information: the clairvoyant, an early warning, and a law that persists (Proposition 9.3; Worked Example 9.1, Step 5; Figure 9.3(b); AXIOM Lab 2.9, step 4)
Quantity | Value | Reading
Volume I's package | 10.4406 | Nothing is read
Clairvoyant: each path's cheapest safe package, the costliest 5% let go (engine) | 0.4367 | $0.44 million (Proposition 9.3(iii))
Expected value of perfect information | 10.0039 | $10.0 million: the most any information could save with these levers
Paths given a package (engine) | 19.62% | 19.6%
Paths that need no lever | 80.38% | Four paths in five
Paths given some of the line (engine) | 16.29% | One in six
Early warning: paths that see a closure during the program (engine) | 25.91% | 26 percent
share with no closure ahead | 74.09%
No closure ahead: line (engine) | 0 | No line
delay (engine) | 0.60835 | 0.61 quarter
chance allotted | 4.75% | 4.75%, on a grid of a quarter of a point
cost | 4.8668 | $4.87 million
Closure ahead: line (engine) | 215 | $215 million
delay (engine) | 0.50438 | Half a quarter
chance allotted, so that the overall chance is 5% | 5.715% | 5.71%: more of the appetite where the closure is coming (Proposition 9.3(ii))
cost | 10.4851 | $10.49 million
Expected cost with the warning | 6.3226 | $6.32 million
The warning is worth | 4.118 | $4.1 million
Reading cash every quarter is worth | 0.24544 | $0.25 million
Persistence 0.85, surprises only: some quarter (engine) | 21.01% | 21.0 percent (8.4 at 0.6)
Persistence 0.85: committed line (engine) | 165 | $165 million
committed delay (engine) | 2.9033 | Almost three quarters
cost | 28.1764 | $28.2 million
Persistence 0.85: reading cash every quarter, cost (engine) | 25.8815 | Line 160, 1.9 committed, slowdown 5.0
saves | 2.2949 | $2.3 million
as a share of the package | 8.145% | 8 percent: cash says more when surprises persist
Figure 9.3(b): the least cost by what the decision can see
What the decision can see | Least cost
Nothing (committed) | 10.4406
Cash, every quarter | 10.1952
Warning of closures | 6.3226
Every path's future | 0.4367

## Hiring
Chapter 8's hiring loop with outside events (Theorems 9.1-9.2; Proposition 9.1; Online Appendix 9.B.3; AXIOM Lab 2.9, step 5)
dd = (-a d + b v) dt + sigma dW1 + s v dW2. Certainty equivalence: the Riccati root of Chapter 8, and the departures cost sigma^2 p / rho. Caution: r b K^2 + (r beta + q s^2) K - q b = 0. Vigilance: (b^2/r) p^2 + (beta - c^2) p - q = 0. Robustness: (b^2/r - 2 theta sigma^2) p^2 + beta p - q = 0, smallest positive root.
Quantity | Value | Reading
Riccati root p (certainty equivalence) | 0.00090372 | 0.00090372: departures leave the rule unchanged
Gain K = b p / r, a year | 4.3379 | 4.34 a year
Departures cost sigma^2 p, a year | 0.20334 | $0.20 million a year
in present value, sigma^2 p / rho | 2.1334 | $2.13 million, whatever HR decides
Least cost from 100 short with departures | 11.1706 | 9.037 + 2.133 = 11.171
Caution: an uncertain yield of approvals (Theorem 9.2(iii))
Yield noise s | r b | r beta + q s^2 | q b | Gain K | p = q/(bK + beta) | Least cost p(d0^2 + sigma^2/rho) | Certainty-equivalent gain's cost | Ignoring the uncertainty costs
0.1 | 7.5e-05 | 0.00014927 | 0.00192 | 4.1614 | 0.00093157 | 11.5149 | 11.5236 | 0.0086789
0.2 | 7.5e-05 | 0.00024527 | 0.00192 | 3.6821 | 0.0010167 | 12.567 | 12.7303 | 0.16332
Vigilance: p with noise c d dW (Theorem 9.2(iv)) | 0.00094136 | 0.00094136
gain b p / r | 4.5185 | 4.52: close a gap faster when it breeds its own volatility
Robustness: guarding against a misjudged drift at the penalty h^2/(2 theta) a year (Proposition 9.1(ii))
theta | b^2/r - 2 theta sigma^2 | Discriminant | p (smallest positive root) | p x 1e4 | Gain K
0 | 2880 | 37.7442 | 0.00090372 | 9.0372 | 4.3379
1 | 2430 | 31.9842 | 0.00097063 | 9.7063 | 4.659
2 | 1980 | 26.2242 | 0.0010563 | 10.5625 | 5.07
3 | 1530 | 20.4642 | 0.0011717 | 11.7175 | 5.6244
6 | 180 | 3.1842 | 0.0023507 | 23.5067 | 11.2832
6.5 | -45 | 0.30421 | 0.004296 | 42.9604 | 20.621
b^2/r - 2 theta sigma^2 turns negative at theta | 6.4 | 6.4: the robust rule continues past it
Breakdown point theta-bar = (b^2/r + beta^2/(4q)) / (2 sigma^2) | 6.5528 | 6.553: past it no linear rule has a finite worst case
At the breakdown, p -> 2q/beta | 0.0068216 | 0.006822
and K -> | 32.7438 | 32.7
The value ledger (Theorem 9.1(iii)): E M_t, booked with the best rule's value p d^2 + sigma^2 p / rho
Rule | Gain K | g = a + bK | q + r K^2 | m = sigma^2/(2g) | Years t | E d_t^2 | Value earned to t | Expected ledger E M_t
Best rule | 4.3379 | 3.0242 | 0.0055521 | 37.2004 | 0 | 10000 | 0 | 11.1706
Best rule | 4.3379 | 3.0242 | 0.0055521 | 37.2004 | 1 | 60.7308 | 9.1813 | 11.1706
Best rule | 4.3379 | 3.0242 | 0.0055521 | 37.2004 | 2 | 37.256 | 9.3797 | 11.1706
Best rule | 4.3379 | 3.0242 | 0.0055521 | 37.2004 | 5 | 37.2004 | 9.8251 | 11.1706
Best rule: the limit, the rule's own cost | 4.3379 | 3.0242 | 0.0055521 | 37.2004 |  |  |  | 11.1706
Volume I's cautious gain | 2 | 1.6214 | 0.0037 | 69.3827 | 0 | 10000 | 0 | 11.1706
Volume I's cautious gain | 2 | 1.6214 | 0.0037 | 69.3827 | 1 | 457.1843 | 10.861 | 13.1761
Volume I's cautious gain | 2 | 1.6214 | 0.0037 | 69.3827 | 2 | 84.5268 | 11.4605 | 13.2868
Volume I's cautious gain | 2 | 1.6214 | 0.0037 | 69.3827 | 5 | 69.3836 | 12.028 | 13.3916
Volume I's cautious gain: the limit, the rule's own cost | 2 | 1.6214 | 0.0037 | 69.3827 |  |  |  | 13.7004
Along the best rule the expected ledger stays at the least cost: no drift. Under the cautious gain it drifts up toward that rule's own cost, revealing a rule that is not the declared one.

## Reference_Values
Checkpoint | Engine value | Meaning (where in the book)
Planned liquidity at its low point | 481.9504 | Volume I, Chapter 8: $482 million in quarter 7
A quarter of delay lifts the deepest point by | 24.8 | $24.8 million
Gaussian chance, quarter 7 | 0.017342 | Online Appendix 9.B.2: 1.73%
Gaussian chance, quarter 12 | 0.0051322 | 0.51%
Sum over the quarters, Gaussian | 0.11165 | Figure 9.1: 11.2%
Draw still ahead after quarter 3 | 0.29941 | 29.9%
Draw still ahead after quarter 6 | 0.036981 | 3.7%
Committed package: the cheapest line | 170 | $170 million
Committed package: fees | 5.1 | $5.10 million
Committed package: delay cost | 5.3406 | $5.34 million
Committed package: cost | 10.4406 | $10.44 million
Standard error of 5% on 100,000 paths | 0.0006892 | 0.069 points
Fresh chance below 5%, standard errors | 1.3494 | Within 1.3 standard errors
Designed on the fresh paths: cost | 10.2761 | $10.28 million
Read quarter by quarter: cost | 1.8605 | $1.86 million
CVaR package: cost | 18.3142 | $18.31 million
Convexity gives up | 7.8736 | $7.9 million
A nonconvex quantile: chance at the midpoint | 0.0784 | 0.0784
kappa at a quarter-point margin | 6.6855e-05 | 6.69e-5
Chernoff bound, quarter point, 100,000 paths | 0.0012489 | 0.12 percent
Chernoff bound, quarter point, 10,000 paths | 0.51245 | 0.51
Hoeffding bound, quarter point, 100,000 paths | 0.2865 | 0.29
Hoeffding bound, quarter point, 10,000 paths | 0.8825 | 0.88
kappa at one point | 0.0011267 | 0.00113
Chernoff bound, one point, 1,000 paths | 0.3241 | Up to 32 percent
Chernoff bound, two points, 1,000 paths | 0.0075645 | 0.0076
Slow only, quarter 1: cost | 10.618 | Table 9.3: 10.62
Slow only, quarter 2: cost | 10.8894 | 10.89
Slow only, quarter 3: cost | 11.4064 | Table 9.3: 11.41
Slow only, quarter 4: cost | 12.3057 | 12.31
Commit and slow, quarter 1: cost | 10.3788 | 10.38
Commit and slow, quarter 2: cost | 10.2979 | 10.30
Commit and slow, quarter 3: cost | 10.2334 | Table 9.3: 10.23
Commit and slow, quarter 4: cost | 10.3054 | 10.31
Commit and slow, quarter 5: cost | 10.3487 | 10.35
Commit and slow, quarter 6: cost | 10.4289 | 10.43
The best quarter to read | 3 | Quarter 3
Quarter 3 rule saves against the package | 0.20718 | $0.21 million
Every quarter: contingent delay | 0.15565 | 0.16 quarter
Every quarter: cost | 10.1952 | Table 9.3: 10.20
Every quarter: saves against the package | 0.24544 | $0.25 million
Every quarter: saves, share | 0.023508 | 2 percent
Expected value of perfect information | 10.0039 | $10.0 million
Early warning, none ahead: cost | 4.8668 | 4.87
Early warning, closure ahead: chance | 0.057148 | 5.71%
Early warning, closure ahead: cost | 10.4851 | 10.49
Early warning: expected cost | 6.3226 | Table 9.3: 6.32
Early warning: worth | 4.118 | $4.1 million
Persistence 0.85: committed cost | 28.1764 | $28.2 million
Persistence 0.85: reading cash saves | 2.2949 | $2.3 million
Persistence 0.85: saves, share | 0.081449 | 8 percent
Hiring: Riccati root p | 0.00090372 | 0.00090372
Hiring: gain K | 4.3379 | 4.34 a year
Hiring: departures cost a year | 0.20334 | $0.20 million
Hiring: departures cost in present value | 2.1334 | $2.13 million
Hiring: least cost with departures | 11.1706 | $11.171 million
Hiring: beta | 0.93819 | 0.938194
Caution, s = 0.10: gain | 4.1614 | 4.16
Caution, s = 0.10: p | 0.00093157 | 0.00093157
Caution, s = 0.10: least cost | 11.5149 | 11.515
Caution, s = 0.20: gain | 3.6821 | 3.68
Caution, s = 0.20: p | 0.0010167 | 0.00101669
Caution, s = 0.20: least cost | 12.567 | 12.567
Certainty-equivalent gain at s = 0.10: cost | 11.5236 | 11.524
Certainty-equivalent gain at s = 0.20: cost | 12.7303 | 12.730
Ignoring the yield's uncertainty costs, s = 0.10 | 0.0086789 | $0.01 million
Ignoring the yield's uncertainty costs, s = 0.20 | 0.16332 | $0.16 million
Vigilance, c = 0.5: p | 0.00094136 | 0.00094136
Vigilance, c = 0.5: gain | 4.5185 | 4.5185
Robust, theta = 1: gain | 4.659 | 4.66
Robust, theta = 2: gain | 5.07 | 5.07
Robust, theta = 3: gain | 5.6244 | 5.624
Robust, theta = 6: gain | 11.2832 | 11.283
Robust, theta = 6.5: gain | 20.621 | 20.621
Robust, theta = 1: p x 1e4 | 9.7063 | 9.706
Robust, theta = 6.5: p x 1e4 | 42.9604 | 42.960
b^2/r - 2 theta sigma^2 turns negative at | 6.4 | 6.4
Breakdown point theta-bar | 6.5528 | 6.553
At the breakdown, p -> 2q/beta | 0.0068216 | 0.006822
At the breakdown, K -> | 32.7438 | 32.7
Ledger, best rule, at 0 | 11.1706 | 11.171
Ledger, best rule, after 1 year | 11.1706 | 11.171: no drift
Ledger, best rule, after 5 years | 11.1706 | 11.171
Ledger, cautious gain, after 1 year | 13.1761 | 13.176
Ledger, cautious gain, after 2 years | 13.2868 | 13.287
Ledger, cautious gain, after 5 years | 13.3916 | 13.392
Ledger, cautious gain, its limit | 13.7004 | 13.700, the rule's own cost

## Checks
Checkpoint | Workbook formula value | Engine value | ¦diff¦ | Tolerance | Status
Planned liquidity at its low point | 481.9504 | 481.9504 | 0 | 1e-09 | PASS
A quarter of delay lifts the deepest point by | 24.8 | 24.8 | 0 | 1e-09 | PASS
Gaussian chance, quarter 7 | 0.017342 | 0.017342 | 0 | 1e-12 | PASS
Gaussian chance, quarter 12 | 0.0051322 | 0.0051322 | 0 | 1e-12 | PASS
Sum over the quarters, Gaussian | 0.11165 | 0.11165 | 0 | 1e-12 | PASS
Draw still ahead after quarter 3 | 0.29941 | 0.29941 | 0 | 1e-12 | PASS
Draw still ahead after quarter 6 | 0.036981 | 0.036981 | 0 | 1e-12 | PASS
Committed package: the cheapest line | 170 | 170 | 0 | 0 | PASS
Committed package: fees | 5.1 | 5.1 | 0 | 1e-09 | PASS
Committed package: delay cost | 5.3406 | 5.3406 | 0 | 1e-09 | PASS
Committed package: cost | 10.4406 | 10.4406 | 0 | 1e-09 | PASS
Standard error of 5% on 100,000 paths | 0.0006892 | 0.0006892 | 0 | 1e-12 | PASS
Fresh chance below 5%, standard errors | 1.3494 | 1.3494 | 0 | 1e-09 | PASS
Designed on the fresh paths: cost | 10.2761 | 10.2761 | 0 | 1e-09 | PASS
Read quarter by quarter: cost | 1.8605 | 1.8605 | 0 | 1e-09 | PASS
CVaR package: cost | 18.3142 | 18.3142 | 0 | 1e-09 | PASS
Convexity gives up | 7.8736 | 7.8736 | 0 | 1e-09 | PASS
A nonconvex quantile: chance at the midpoint | 0.0784 | 0.0784 | 0 | 1e-12 | PASS
kappa at a quarter-point margin | 6.6855e-05 | 6.6855e-05 | 0 | 1e-15 | PASS
Chernoff bound, quarter point, 100,000 paths | 0.0012489 | 0.0012489 | 0 | 1e-12 | PASS
Chernoff bound, quarter point, 10,000 paths | 0.51245 | 0.51245 | 0 | 1e-12 | PASS
Hoeffding bound, quarter point, 100,000 paths | 0.2865 | 0.2865 | 0 | 1e-12 | PASS
Hoeffding bound, quarter point, 10,000 paths | 0.8825 | 0.8825 | 0 | 1e-12 | PASS
kappa at one point | 0.0011267 | 0.0011267 | 0 | 1e-15 | PASS
Chernoff bound, one point, 1,000 paths | 0.3241 | 0.3241 | 0 | 1e-12 | PASS
Chernoff bound, two points, 1,000 paths | 0.0075645 | 0.0075645 | 0 | 1e-12 | PASS
Slow only, quarter 1: cost | 10.618 | 10.618 | 0 | 1e-09 | PASS
Slow only, quarter 2: cost | 10.8894 | 10.8894 | 0 | 1e-09 | PASS
Slow only, quarter 3: cost | 11.4064 | 11.4064 | 0 | 1e-09 | PASS
Slow only, quarter 4: cost | 12.3057 | 12.3057 | 0 | 1e-09 | PASS
Commit and slow, quarter 1: cost | 10.3788 | 10.3788 | 0 | 1e-09 | PASS
Commit and slow, quarter 2: cost | 10.2979 | 10.2979 | 0 | 1e-09 | PASS
Commit and slow, quarter 3: cost | 10.2334 | 10.2334 | 0 | 1e-09 | PASS
Commit and slow, quarter 4: cost | 10.3054 | 10.3054 | 0 | 1e-09 | PASS
Commit and slow, quarter 5: cost | 10.3487 | 10.3487 | 0 | 1e-09 | PASS
Commit and slow, quarter 6: cost | 10.4289 | 10.4289 | 0 | 1e-09 | PASS
The best quarter to read | 3 | 3 | 0 | 0 | PASS
Quarter 3 rule saves against the package | 0.20718 | 0.20718 | 1.7208e-15 | 1e-09 | PASS
Every quarter: contingent delay | 0.15565 | 0.15565 | 0 | 1e-09 | PASS
Every quarter: cost | 10.1952 | 10.1952 | 0 | 1e-09 | PASS
Every quarter: saves against the package | 0.24544 | 0.24544 | 0 | 1e-09 | PASS
Every quarter: saves, share | 0.023508 | 0.023508 | 0 | 1e-12 | PASS
Expected value of perfect information | 10.0039 | 10.0039 | 0 | 1e-09 | PASS
Early warning, none ahead: cost | 4.8668 | 4.8668 | 0 | 1e-09 | PASS
Early warning, closure ahead: chance | 0.057148 | 0.057148 | 0 | 1e-12 | PASS
Early warning, closure ahead: cost | 10.4851 | 10.4851 | 0 | 1e-09 | PASS
Early warning: expected cost | 6.3226 | 6.3226 | 0 | 1e-09 | PASS
Early warning: worth | 4.118 | 4.118 | 0 | 1e-09 | PASS
Persistence 0.85: committed cost | 28.1764 | 28.1764 | 0 | 1e-09 | PASS
Persistence 0.85: reading cash saves | 2.2949 | 2.2949 | 0 | 1e-09 | PASS
Persistence 0.85: saves, share | 0.081449 | 0.081449 | 0 | 1e-12 | PASS
Hiring: Riccati root p | 0.00090372 | 0.00090372 | 0 | 1e-13 | PASS
Hiring: gain K | 4.3379 | 4.3379 | 0 | 1e-09 | PASS
Hiring: departures cost a year | 0.20334 | 0.20334 | 0 | 1e-09 | PASS
Hiring: departures cost in present value | 2.1334 | 2.1334 | 0 | 1e-09 | PASS
Hiring: least cost with departures | 11.1706 | 11.1706 | 0 | 1e-09 | PASS
Hiring: beta | 0.93819 | 0.93819 | 0 | 1e-12 | PASS
Caution, s = 0.10: gain | 4.1614 | 4.1614 | 0 | 1e-09 | PASS
Caution, s = 0.10: p | 0.00093157 | 0.00093157 | 0 | 1e-13 | PASS
Caution, s = 0.10: least cost | 11.5149 | 11.5149 | 0 | 1e-09 | PASS
Caution, s = 0.20: gain | 3.6821 | 3.6821 | 0 | 1e-09 | PASS
Caution, s = 0.20: p | 0.0010167 | 0.0010167 | 0 | 1e-13 | PASS
Caution, s = 0.20: least cost | 12.567 | 12.567 | 0 | 1e-09 | PASS
Certainty-equivalent gain at s = 0.10: cost | 11.5236 | 11.5236 | 0 | 1e-09 | PASS
Certainty-equivalent gain at s = 0.20: cost | 12.7303 | 12.7303 | 0 | 1e-09 | PASS
Ignoring the yield's uncertainty costs, s = 0.10 | 0.0086789 | 0.0086789 | 0 | 1e-09 | PASS
Ignoring the yield's uncertainty costs, s = 0.20 | 0.16332 | 0.16332 | 0 | 1e-09 | PASS
Vigilance, c = 0.5: p | 0.00094136 | 0.00094136 | 0 | 1e-13 | PASS
Vigilance, c = 0.5: gain | 4.5185 | 4.5185 | 0 | 1e-09 | PASS
Robust, theta = 1: gain | 4.659 | 4.659 | 0 | 1e-09 | PASS
Robust, theta = 2: gain | 5.07 | 5.07 | 0 | 1e-09 | PASS
Robust, theta = 3: gain | 5.6244 | 5.6244 | 0 | 1e-09 | PASS
Robust, theta = 6: gain | 11.2832 | 11.2832 | 0 | 1e-09 | PASS
Robust, theta = 6.5: gain | 20.621 | 20.621 | 0 | 1e-09 | PASS
Robust, theta = 1: p x 1e4 | 9.7063 | 9.7063 | 0 | 1e-09 | PASS
Robust, theta = 6.5: p x 1e4 | 42.9604 | 42.9604 | 0 | 1e-09 | PASS
b^2/r - 2 theta sigma^2 turns negative at | 6.4 | 6.4 | 0 | 1e-09 | PASS
Breakdown point theta-bar | 6.5528 | 6.5528 | 0 | 1e-09 | PASS
At the breakdown, p -> 2q/beta | 0.0068216 | 0.0068216 | 0 | 1e-12 | PASS
At the breakdown, K -> | 32.7438 | 32.7438 | 0 | 1e-09 | PASS
Ledger, best rule, at 0 | 11.1706 | 11.1706 | 0 | 1e-09 | PASS
Ledger, best rule, after 1 year | 11.1706 | 11.1706 | 0 | 1e-09 | PASS
Ledger, best rule, after 5 years | 11.1706 | 11.1706 | 0 | 1e-09 | PASS
Ledger, cautious gain, after 1 year | 13.1761 | 13.1761 | 0 | 1e-09 | PASS
Ledger, cautious gain, after 2 years | 13.2868 | 13.2868 | 0 | 1e-09 | PASS
Ledger, cautious gain, after 5 years | 13.3916 | 13.3916 | 0 | 1e-09 | PASS
Ledger, cautious gain, its limit | 13.7004 | 13.7004 | 0 | 1e-09 | PASS
All checkpoints |  |  |  |  | ALL PASS